## Datasheet
DATASHEET FOR PROJECT MANAGEMENT & EXECUTION SOLUTION
SN | REQUIREMENTS from the PLATFORM | Vendor Confirmation (Yes/No) | Vendor Offering Gist | Enclosures / Supporting Docs.
1 | Project Planning & Scheduling
1.1 | Integration with MS Projects
1.2 | Integration with Primavera P6
1.3 | Importing / Prepartion of Complete Project Schedule in Platform
1.4 | Defining Project Milestones with Tracking, Progress & Reports
1.5 | Provision to update the Project Schedule as required
1.6 | Critical Path Monitoring & Analysis
1.7 | Schedule Delay Capture & Analysis
1.8 | Schedule Delay Catch Up Plan
2 | Procurement
2.1 | Procurement Planning & Schedule Integration
2.2 | Listing of Orders from all Functions like Civil, Mech, E&I (Packages, Individual)
2.3 | Complete Procurement Status (All Orders & Contracts)
2.4 | Critical Orders Tracking
2.5 | Shipment Tracking
2.6 | Customs Clearance Tracking
2.7 | LD & Force Majoure Monitoring
2.8 | Change Order Management
2.9 | Claims Management
3 | Engineering
3.1 | Engineering Schedule Integration (All Functions)
3.2 | Master Document List Integration (All Functions)
3.3 | Engineering Progress Tracking (All Functions)
3.4 | Drawing & Document Management (All Functions)
3.5 | Drawings Review & Approval Workflow (RCCPL & Vendor)
3.6 | Interface Management between Functions / Vendors
3.7 | Change Request Management & Resolution
3.8 | GFC Drawings Release
3.9 | Revision Control
3.1 | Access to GFC Dwgs on Mobile to all Stake holders (App)
3.11 | Technical Query Management for all Stake holders (App)
3.12 | Query Escalation Matrix
3.13 | Gap Analysis between Dwgs Revisions
4 | Construction
4.1 | Construction Schedule Integration (All Functions)
4.2 | Site Mobilization Tracking
4.3 | Daily Progress Reporting
4.4 | Weekly Progress Reporting
4.5 | Quantity Tracking
4.6 | Productivity Monitoring
4.7 | Work Front Release
4.8 | Site Instructions Management
4.9 | Construction Change Management
4.1 | RFI Management
4.11 | NCR Management
4.12 | Site Resource Tracking
4.13 | Equipment Utilization Monitoring
4.14 | Contractor Performance Monitoring
5 | Quality
5.1 | Quality Management Plan Integration (All Functions)
5.2 | TPI Quality Inspection Reports Intergration & Scheduling
5.3 | Factory Acceptance Tests Monitoring
5.4 | Site Acceptance Tests
5.5 | NCR Management
5.6 | Corrective Action Tracking
5.7 | Root Cause Analysis for NCRs
5.8 | Vendor Quality Monitoring
5.9 | Concrete Pour Card Monitoring
5.1 | Welding Quality Records
5.11 | Calibration Records
5.12 | IBR Testing
6 | Health Safety & Enviornment
6.1 | OHS Manual Complaince Integration
6.2 | Permit-to-Work System Integration
6.3 | Toolbox Talks Integration
6.4 | Safety Observation Tour Integration
6.5 | Incident Reporting Integration
6.6 | Near-Miss Reporting Integration
6.7 | HIRA & HAZOP Integration
6.8 | Safety Audits Reports Integration
6.9 | Emergency Response Management
7 | Commissioning & Handover
7.1 | Mechanical Completion Tracking
7.2 | E&I Completion Tracking
7.3 | Pre-Commissioning Tracking
7.4 | No Load Trails
7.5 | Load Trails
7.6 | Commissioning Procedure Management
7.7 | Cold & Hot Commissioning
7.8 | Performance Testing
7.9 | Punch List Closure
7.1 | O&M Manual Handover
7.11 | Training Record Management
7.12 | Final Acceptance Certification
8 | IT Technology Evaluation
8.1 | Cloud or On-Premise Deployment
8.2 | Storage & Network Speed requirement?
8.3 | Cybersecurity Complaince
8.4 | Mobile App & Accessibility
8.5 | Offline Capability
8.6 | API Availability
8.7 | Multi-language Support ?
8.8 | User Management & Access Control / Authorization?
8.9 | User Licenses Limited or Umlimited?
8.1 | NDA Agreement
8.11 | Data Backup Availability?
8.12 | SAP Integration
8.13 | MSP Integration
8.14 | Primavera P6 Integration
8.15 | Power BI Integration
8.16 | DCS/OPC/SCADA Integration?
8.17 | AI Chatbot Availability?
8.18 | What is the maximum number of concurrent users supported?
8.19 | Can project data be extracted completely if the contract ends?
8.2 | Is there any vendor lock-in?
8.21 | What are the API rate limits?
8.22 | Does the solution support SSO with Microsoft Entra ID (Azure AD)?
8.23 | Can the solution integrate with SAP ECC 6.0?
8.24 | What AI/LLM model powers the chatbot? What are the Security and Network Architecture Considerations for AI?
8.25 | How is customer data isolated in SaaS deployments?
8.26 | What are the RPO(Recovery Point Objective) and RTO (Recovery Time Objective)commitments, Data backup & Archival Policies?
9 | Reporting & Analytics (All Real time Dashboards & Reports)
9.1 | Executive Dashboards (Real time)
9.2 | Project Dashboards (Real time)
9.3 | KPI Monitoring (Real time)
9.4 | Schedule Analytics
9.5 | Cost Analytics
9.6 | Procurement Analytics
9.7 | Engineering Analytics
9.8 | Construction Analytics
9.9 | Drill-Down Reporting (Real time)
9.1 | Custom Report Builder
10 | Vendor Evaluation
10.1 | Industry Experience
10.2 | Cement Plant Experience
10.3 | EPC Project Experience
10.4 | Global References
10.5 | Indian References
10.6 | Financial Strength
10.7 | Product Roadmap
10.8 | Local Support Capability
10.9 | Training Capability
10.1 | Implementation Team Strength & Site Deployment
11 | Commercial Evaluation
11.1 | License Cost Evaluation
11.2 | Subscription Cost Evaluation
11.3 | Implementation Cost
11.4 | Integration Cost
11.5 | Customization Cost
11.6 | Training Cost
11.7 | Annual Support Cost
11.8 | Additional User Cost
11.9 | Total Cost of Ownership (5 Years)